## Slide 1: Leadership and Governance

## Slide 2
Document Output | Activity | Responsible Person | Timeline
School Improvement Plan | Crafting and Approval of School Improvement Plan PIAs identified Planning Worksheet Plan Design | SGC, SPT, Project Teams, School Monitoring Team, all other stakeholders Program/Process Owners | Start of the SIP Duration
Annual Implementation Plan Year 1 | Cull-out PIAs and activities identified for the first year from Planning Worksheet | SGC, SPT, Project Teams Program/Process Owners | Start of Year 1 implementation of SIP
SMEA Report Adjusted/Catch-up Plans | Conduct SMEA cum PIR on a quarterly basis using template | School Monitoring Team SGC, SPT, Project Teams Program/Process Owners | Every end of the Quarter
School Report Card | Prepare School Report Card | School Monitoring Team LIS Coordinator | Semestral

## Slide 3
Document Output | Activity | Responsible Person | Timeline
School Improvement Plan (updated) | Revisit SIP PIAs identified Planning Worksheet Plan Design | SGC, SPT, Project Teams, School Monitoring Team, all other stakeholders Program/Process Owners | October (Before crafting of AIP Yr 2)
Annual Implementation Plan Year 2 | Cull-out PIAs and activities identified for the first year from Planning Worksheet | SGC, SPT, Project Teams Program/Process Owners | January (Year 2)
SMEA Report Adjusted/Catch-up Plans | Conduct SMEA cum PIR on a quarterly basis using template | School Monitoring Team SGC, SPT, Project Teams Program/Process Owners | Every end of the Quarter
School Report Card | Prepare School Report Card | School Monitoring Team LIS Coordinator | Semestral

## Slide 4
Document Output | Activity | Responsible Person | Timeline
School Improvement Plan (updated) | Revisit SIP PIAs identified Planning Worksheet Plan Design | SGC, SPT, Project Teams, School Monitoring Team, all other stakeholders Program/Process Owners | October (Before crafting of AIP Yr 3)
Annual Implementation Plan Year 3 | Cull-out PIAs and activities identified for the first year from Planning Worksheet | SGC, SPT, Project Teams Program/Process Owners | January (Year 3)
SMEA Report Adjusted/Catch-up Plans | Conduct SMEA cum PIR on a quarterly basis using template | School Monitoring Team SGC, SPT, Project Teams Program/Process Owners | Every end of the Quarter
School Report Card | Prepare School Report Card | School Monitoring Team LIS Coordinator | Semestral

## Slide 5: Important Forms and Data Sources
Annex 1a – School-Community Data Template
Annex 1b – Child Mapping Tool
Annex 2a – Child Friendly School Survey
Annex 2b – Child Protection Policy Implementation Checklist
Annex 2c – Student Led School Watching and Hazard Mapping
Annex 3 – Gap Analysis
Annex 4 – Identifying Priority Improvement Areas
Annex 5 - Planning Worksheet
Annex 9 – Project Work Plan and Budget Matrix
Annex 10 – Annual Implementation Plan
Annex 11 – SRC Summary of Information